## Slide 1: The Mythical Man-Month
20150888, CSE, Kanghee Park

## Slide 2: Chapter 2: The Mythical Man-Month
Why software project have gone awry for lack of calendar time?
  Techniques of estimating are porly developed
  Confuse efforts with progress
  Lack the courteous stubbornness of Antoine’s chef (Good cooking takes time)
  Schedule progress is poorly monitored
  Add manpower when schedule slippage is recognized

## Slide 3: Chapter 2: The Mythical Man-Month
All programmers are optimists
  Scheduling under false assumption ‘all will go well’
  Our ideas become clear only during implementation
  We expect few difficulties on implementation
Progress does not vary as (# of men) * (# of month)
Perfectly
Partitionable task
Unpartitionable task
Task with complex
interrelationships
Partitionable task
Requiring communication

## Slide 4: Chapter 2: The Mythical Man-Month
Scheduling a software task
  1/3 planning, 1/6 coding
  ¼ component test and early system test
  ¼ system test
Adding manpower to a late software project make it later
  New men requires training
  Repartitioning and system test effects

## Slide 5: Chapter 3: The Surgical Team
The surgeon
  Personally defines the functional and performance specifications,
  Designs the program, codes it, tests it,
  And writes its documentation
  Needs talent, experience, and considerable systems and application knowledge
The copilot
  Alter ego of the surgeon, able to do any part of job, but is less experienced
  Share in the design as a thinker, discussant, and evaluator
The administrator
  Handles money, people, space, and machines
  Interfaces with the administrative machinery of the rest of the organization

## Slide 6: Chapter 3: The Surgical Team
The administrator
  Handles money, people, space, and machines
  Interfaces with the administrative machinery of the rest of the organization
The editor
  Takes the draft or dictated manuscript produced by the surgeon
  And criticizes it, reworks it, provides it with references and bibliography,
  Nurses it through several versions, and oversees the mechanics of production
Two secretaries (for the administrator and the editor)

## Slide 7: Chapter 3: The Surgical Team
The program clerk
  Maintain all the technical records of the team in a programming-product library
  Make all the computers runs visible to team members and identifying all programs and data as team property
The toolsmith
  Ensure adequacy of the basic service and constructing, maintaining,
  and upgrading special tools needed by his team

## Slide 8: Chapter 3: The Surgical Team
The tester
  Devises system test cases from the functional specs,
  Is an assistant who devises test data for the day-by-day debugging
  Plan testing sequences and set up the scaffolding required component tests
The language lawyer
  Find a neat and efficient way to use the language to do difficult, obscure, or tricky things

## Slide 9: Chapter 3: The Surgical Team